## T3 Company (BRD)
Application | No. | Obstacle/ Business Requirements | Type | Proposed solution | Initiation Date | Estimated completion date | Completion date | Current status | Assigned to | Result
1. Inventory | 1 | Implement a structured inventory system. | New Feature | Define Inventory Organization (T3 Inv Org) | 2025-01-03 | 2025-03-03 | 2025-03-03 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 2 | Establish distinct areas for storage, receiving, and shipping. | New Feature | Define Subinventories (Main Warehouse,Receiving Area, Staging Area) | 2025-01-03 | 2025-03-03 | 2025-03-03 | Closed | Aml Mohammed Dweeny | Completed
1. Inventory | 3 | Enable precise tracking of high-value item locations within the main warehouse. | New Feature | Define Stock Locators Key Flexfield with 3 Segments (Aisle, Rack, Bin) | 2025-01-03 | 2025-03-03 | 2025-03-05 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 4 | Enable items classification based on categories for reporting, costing, and analysis. | New Feature | Configure Item Categories Key Flexfield reflecting the business hierarchy. | 2025-01-03 | 2025-03-03 | 2025-03-06 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 5 | Standardize item categorization for efficient searches and reporting. | New Feature | Configure Item Categories (PCs, Laptops, Accessories) | 2025-01-03 | 2025-03-03 | 2025-03-07 | Closed | Aml Mohammed Dweeny | Completed
1. Inventory | 6 | classifiy inventory between active stock,and stock items that is obselete. | New Feature | Define Item Status (Active, inActive) | 2025-01-03 | 2025-03-07 | 2025-03-08 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 7 | Establish item behaviors and simplify bulk item creation. | New Feature | Create item templates to pre-populate common attribute values. | 2025-01-03 | 2025-03-07 | 2025-03-08 | Closed | Sabreen Hassan | Completed
1. Inventory | 8 | Standardize quantity measurement units and conversions. | New Feature | Define quantity base UOM and derived units with conversion rates. | 2025-01-03 | 2025-03-07 | 2025-03-05 | Closed | Rehab Abuelabbas | Completed
1. Inventory | 9 | Need to facilitate transactions mapping to proper accounts | New Feature | Define a new Shorthand Account Aliase | 2025-01-03 | 2025-03-10 | 2025-03-10 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 10 | Establish a clear inventory costing methodology. | New Feature | Configure Costing Method (Average Costing ) | 2025-01-03 | 2025-03-03 | 2025-03-03 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 11 | the system must calculate the total cost of items | New Feature | Define cost sub-elements (handling and duties) to ensure all additional costs are accounted for. | 2025-01-03 | 2025-03-22 | 2025-04-02 | Closed | Aml Mohammed Dweeny | Completed
1. Inventory | 12 | Enforce inventory transaction rules based on warehouse operations. | New Feature | Configure Custom Transaction Types | 2025-01-03 | 2025-03-23 | 2025-04-02 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 13 | Configure rules to regulate inventory transactions and Prevent invalid item issues. | New Feature | Define Material Status to allow only the custom transaction types according to sub-inventory operations | 2025-01-03 | 2025-03-24 | 2025-04-02 | Closed | Sobhey Saied Farhan | Completed
1. Inventory | 14 | Allow transactions to be posted within valid periods. | New Feature | Open required Accounting Periods in Inventory & Close periods post-reconciliation. | 2025-01-03 | 2025-03-15 | 2025-03-15 | Closed | Rehab Abuelabbas | Completed
1. Inventory | 15 | New users lack ERP knowledge, causing delays and errors in inventory transactions. Thus, Needs guidance or training materials | New Feature | Develop Inventory User Guide | 2025-01-03 | 2025-03-30 | 2025-03-30 | Closed | Rehab- Sabreen- Aml | Completed
1. Inventory | 16 | Automate Refilling process for transport vehicles | New Feature | Implement Min-Max Planning Process For these vehicles to be refilled from the Main Warehouse | 2025-01-03 | 2025-03-30 | 2025-03-30 | Closed | Rehab- Sabreen- Aml | Completed
1. Inventory | 16 | Ensure Proper reports are provided for inventory transactions and it's value. | New Feature | Define Key Inventory & Costing Reports Parameters | 2025-01-03 | 2025-03-30 | 2025-04-20 | Closed | Sobhey Saied Farhan | Completed
2. Purchasing | 17 | Establish a structured process to differentiate purchasing activities | New Feature | Define Document Types (Purchase Requisition, Purchase Order) | 2025-01-03 | 2025-03-19 | 2025-03-19 | Closed | Sabreen Hassan | Completed
2. Purchasing | 18 | Establish automatic numbering of purchasing documents | New Feature | Define Organization: Purchasing Options | 2025-01-03 | 2025-03-20 | 2025-03-20 | Closed | Aml Mohammed Dweeny | Completed
2. Purchasing | 19 | Centralize supplier information management to prevent duplicate records and to keep Suppliers contacts. | New Feature | Implement Supplier Management (Suppliers, Sites, Payment Terms). | 2025-01-03 | 2025-03-20 | 2025-03-20 | Closed | Sobhey Saied Farhan | Completed
2. Purchasing | 20 | Define receiving routing of inbound items to be direct delivery to warehouse | New Feature | Define Organization: Receiving Options | 2025-01-03 | 2025-03-20 | 2025-03-20 | Closed | Aml Mohammed Dweeny | Completed